## Table 1 (2)
REQUEST FOR INSPECTION(RFI)
Name of the Project: | LH-10, Lanco Hills,Manikonda, Hyderabad
Name of the work:
From: | BCIM ENGINEERING PVT.LTD. | RFI / Pourcard no:
to: | Lanco Hills Contractors Pvt Ltd. | Date:
Atten: | Project Manager | Site :
We are requesting for Light Weight Filling :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
We are requesting for Light Weight Filling :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
Ref Doc:
Remarks / Comments:
For Client: (Name & Signature)
Date :

## Table 1
Lanco Hills Contractors Pvt Ltd.
Check list for Light weight filling
Name of The Project : LH-10, Lanco Hills,Manikonda, Hyderabad | [6 empty] | Doc No :LHRP /QA& QC /LW /01/R0 / 001
Location :Lanco Hills,Manikonda, Hyderabad | [6 empty] | Check List No :
Date of Opening :
Sl No | Points to be Checked |  |  |  | Inspections |  |  |  | Remarks
[5 empty] | Inspection 1 |  | Inspection 2
[5 empty] | Date |  | Date
[5 empty] | / | Action Proposed | / | tatus of Compliance
Pre execution checks
1 | Check the material is approved.
2 | Has the area prepared & kept ready to fill the Light weight material?
3 | Is the methodology is approved?
Checks during execution
1 | The light weight material placing area on slab shall be cleaned and water to be sprinkled.
2 | Check the Laying of light weight material as per methodology.
3 | Check the laying in layers as per approved methodology.
4 | The thickness of joints has to be maintained uniformly (Should be 12-20 mm).
5 | Check the Laying 0f M10 Grade of concrete of specified thickness as approved Boq, per the approved methodology.
Approval for starting execution
Contractors Engineer ( Sign & Name ) |  |  | Contractors QC Engineer ( Sign & Name ) | PMC Engineer ( Sign & Name ) |  |  |  | Client QC Engineer ( Sign & Name )
Post execution checks
1 | Check the level and finish
2 | Curing to be done for at least 7 days.
Final Approval
Approved Approved subjected to listed rectification Not approved ( see Remarks)
Remarks if Any
Contractors Engineer ( Sign & Name ) |  |  | Contractors QC Engineer ( Sign & Name ) | PMC Engineer ( Sign & Name ) |  |  |  | Client QC Engineer ( Sign & Name )