## Table 1 (2)
REQUEST FOR INSPECTION(RFI)
Name of the Project: | LH-10, Lanco Hills,Manikonda, Hyderabad
Name of the work:
From: | BCIM ENGINEERING PVT.LTD. | RFI / Pourcard no:
to: | Lanco Hills Contractors Pvt Ltd. | Date:
Atten: | Project Manager | Site : LH-10,Lanco Hills
We are requesting for WaterProofing :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
We are requesting for WaterProofing :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
Ref Doc:
Remarks / Comments:
For Client: (Name & Signature)
Date :

## Table 1
Lanco Hills Contractors Pvt Ltd.
Check List for Water proofing (Expansion Joint) |  |  |  | Doc No :LHRP /QA& QC / WPS /09 / R0 / 001
Name of The Project : LH-10, Lanco Hills,Manikonda, Hyderabad |  |  |  | Check List No :
Location :Lanco Hills,Manikonda, Hyderabad |  |  |  | Date of Opening :
Sl No | Points to be Checked |  | Inspections |  |  |  | Remarks
|  |  | Inspection 1 |  | Inspection 2
|  |  | Date and time |  | Date and time
|  |  | Y/N | Action Proposed | Y/N | Status of Compliance
A. Pre Checks
1 | Is Approved drawings & Methodology available?
2 | Check for approved drawing/plan showing sequence of waterproofing?
3 | Required Quantity of material should be available.
4 | Required tools should be available for executing this activity.
5 | Surface should be free from dust, cement mortar, debris or other foreign material.
6 | Check for the material to be used is with in its shelf-life.
7 | Check for Manufacturer / Third Party Test Report.
8 | Has the required safety measures taken. (Goggles , Gloves, Gum Shoe etc.,)
9 | Check of other allied MEP & RCC- Civil works completed, exposed rod cutting and unwanted materials are removed from the work location & Check for weather the drain pipes are kept in mother slab?
B. Preparation Works
10 | Check for Bore Packing : Filling the gap between the pipes with Non-Shrink self compacting high strength cementitious flow fill grout /Fosroc Conbextra GP2 cementitious repair mortar for cracks / joints
11 | Joints & Cracks should be treated by cutting 'U' Groove(10mm×10mm) and filled with non-shrink self-compacting high strength cementitious Fosroc Conbextra GP2 cementitious repair mortar for cracks / joints
12 | Check Remove the existing expansion board/filler to a minimum depth of 80 mm. Clean both sides of the joint faces by wire brushing and compressed air blowing to remove all dust, loose material, and old sealant residue. Widen or dress the joint to achieve uniform parallel faces where required.
Approval For Starting Execution
Approved Approved subjected to listed rectification Not approved ( see Remarks)
Contractor Engineer( Sign&Name) |  | Contractor QC Engineer (Sign&Name) | PMC Engineer ( Sign & Name ) |  |  | Client Engineer ( Sign & Name )
D. During Waterproofing
13 | check the Sealent Sikaflex-127 Application (Expansion joint) Using a caulking gun or suitable applicator, fill the joint in a single continuous pass from bottom upward,working the sealant firmly against the backer rod and both joint faces to avoid air entrapment.
14 | Minimum sealant depth: 10 mm; minimum sealant width: equal to joint width. Allow the sealant to cure undisturbed for a minimum of 24 hours before applying the topcoat system over the surrounding wall area
15 | Primer Application : Apply PU Based Water proofing primer "Sikalastic-11Primer W " primer shall be applied in one coat on Slab and extend to the full height of parapetwall with coverage of 100 ml per sqmt.
16 | Check for PU based waterproofing systemSikalastic-562, ensure uniform coverage of 1.5 kg/Sqm in Two coats
17 | Apply 2nd Coat brushbond roofguard Premium cross directon to the first coat
18 | After full curing of the Sikalastic-562 IN two-coat system, apply a protective cement plaster coat (CM 1:4 using M-Sand) of 12–15 mm thickness as the final finishing layer over the coated wall surface
E.POST EXECUTION CHECKS
19 | Post Ponding test should be done for 72 hrs on applied of water proofing coat. | [5 empty] | Start date: End date:
20 | Curing to be done atleast for 7 Days
Remarks if Any
Final Approval
Approved Approved subjected to listed rectification Not approved ( see Remarks)
Contractors Engineer(Sign&Name) |  | Contractor QC Engineer ( Sign & Name ) | PMC Engineer( Sign & Name ) |  |  | Client Engineer ( Sign & Name )