## Table 1
REQUEST FOR INSPECTION(RFI)
Name of the Project: | LH-10, Lanco Hills,Manikonda, Hyderabad
Name of the work:
From: | BCIM ENGINEERING PVT.LTD. | RFI / Pourcard no:
to: | Lanco Hills Contractors Pvt Ltd. | Date:
Atten: | Project Manager | Site : LH-10,Lanco Hills
We are requesting for WaterProofing :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
We are requesting for WaterProofing :
Date : | Time :
BCIM Site Engineer | BCIM QC Engineer PMC Engineer | Client Engineer
Ref Doc:
Remarks / Comments:
For Client: (Name & Signature)
Date :

## Table 1 (2)
Lanco Hills Contractors Pvt Ltd.
Check List for Water proofing (Toilet & Utility) Sunken Areas |  |  |  | Doc No : LHRP /QA& QC / WPS/10/R0 / 001
Name of The Project : LH-10, Lanco Hills,Manikonda, Hyderabad |  |  |  | Check List No :
Location : Lanco Hills,Manikonda, Hyderabad |  |  |  | Date of Opening :
SL No | Points to be checked |  | Inspections |  |  |  |  | Remarks
|  |  | Inspection-1 |  |  | Inspection-2
|  |  | Date- |  |  | Date-
|  |  | / | Action proposed |  | / | Status of compliance
A. Pre Checks
1 | Required Quantity of material should be available.
2 | Required tools should be available for executing this activity.
3 | Surface should be free from dust, cement mortar, debris or other foreign material.
4 | Check for the material to be used is with in its shelf-life.
5 | Check for Manufacturer / Third Party Test Report.
6 | Has the required safety measures taken. (Goggles , Gloves, Gum Shoe etc.,)
B. Preparation Works
7 | Bore packing carried out as per approved methodology.
8 | Surface should be free from dust, cement mortar, debris or other foreign material.
9 | Fine visible cracks/construction joints if any, are cleaned & filled with non shrink Grout GP2.
10 | Protrudung materials like Reinforcement, nails, wooden runners to be removed.
11 | Check for coving/Haunching of suitable size of 50x50mm provided at the junction of slab and wall with CM 1:4 admixed with Conplast 421 IC.
C. Pre Ponding test
10 | Pre Ponding test should be done for 24 hrs to find any leakages. | [6 empty] | Start date: End date:
11 | If any leakages observed, fix PVC nozzles to the concrete slab and pressure grout to be done as per approved methodology.
12 | Once the grout complete cut the nozzles and seal the holes and bring it smooth finish.
Approval For Execution
Approved Approved subjected to listed rectification Not approved ( see Remarks)
Contractor Site Engineer ( Sign & Name ) |  | Contractor QC Engineer ( Sign & Name ) | (PMC Engineer) ( Sign & Name ) |  |  |  | (Client Engineer) ( Sign & Name )
D. Checks during Execution
15 | Dampen the surface before starting of coating application.
16 | Prepration of Brushbond RFX mix is as per Manufacturer recommendations/ TDS.
17 | Application of First Coat with recommended brush @ 1.5kg/sqm total be covered in 2coats
18 | Lay Geofabric cloth after 1st coat and press firmly while the first coat is green
Application of Second coat with recommended brush @ 1.5kg/sqm in 2coats with the interval of 4-6hrs depends upon climatic condition.
18 | Confirm that second coat is applied perpendicular to first coat after reaching dry state.
19 | Coating should be done on the entire horizonatl sutrface and should be extended vertically 600mm above SSL.
E. Protection Plaster.
20 | Ensure that there is no damage to water proofing coat prior to protection plaster
21 | Lay Screed with 12mm aggreegate in mix ratio 1:2:4 admixed with Conplast 421 IC to a thickness of 60mm
E. Post Execution Checks
20 | Curing to be done for at least 7 days.
21 | Post Ponding test should be done for 24 hrs and if any leakges should be treated. | [6 empty] | Start date: End date:
Remarks if Any
Final Approval
Approved Approved subjected to listed rectification |  |  |  |  | Not approved (see Remarks)
Contractor Site Engineer ( Sign & Name ) |  | Contractor QC Engineer ( Sign & Name ) | (PMC Engineer) ( Sign & Name ) |  |  |  | (Client Engineer) ( Sign & Name )