## Table 1
Lanco Hills Contractors Pvt Ltd.
Check List for Water proofing (Toilet , Balcony & Utility) Sunken |  |  |  | Doc No : LHRP /QA& QC / WPS/10/R0 / 001
Name of The Project : LH-10, Lanco Hills,Manikonda, Hyderabad |  |  |  | Check List No :
Location : Lanco Hills,Manikonda, Hyderabad |  |  |  | Date of Opening :
SL No | Points to be checked |  | Inspections |  |  |  |  | Remarks
|  |  | Inspection-1 |  |  | Inspection-2
|  |  | Date- |  |  | Date-
|  |  | / | Action proposed |  | / | Status of compliance
A. Pre Checks
1 | Required Quantity of material should be available.
2 | Required tools should be available for executing this activity.
3 | Surface should be free from dust, cement mortar, debris or other foreign material.
4 | Check for the material to be used is with in its shelf-life.
5 | Check for Manufacturer / Third Party Test Report.
6 | Has the required safety measures taken. (Goggles , Gloves, Gum Shoe etc.,)
B. Preparation Works
7 | Bore packing carried out as per approved methodology.
8 | Surface should be free from dust, cement mortar, debris or other foreign material.
9 | Fine visible cracks/construction joints if any, open with U groove(10x10mm) and filled with non shrink Grout GP2.
10 | Protrudung materials like Reinforcement, nails, wooden runners to be removed.
11 | Check all wall-floor junctions, cut a 12mmx12mm along the junction line before coving. Clean the groove and fill with fosroc conbextra GP2 and allow to cure
12 | Check for coving/Haunching of suitable size of 50x50mm provided at the junction of slab and wall with polymer modified CM 1:4 Mortar admixed with conplast 421 IC.
C. Pre Ponding test
13 | Pre Ponding test should be done for 24 hrs to find any leakages. | [6 empty] | Start date: End date:
14 | If any leakages observed, fix PVC nozzles to the concrete slab and pressure grout to be done as per approved methodology.
15 | Once the grout complete cut the nozzles and seal the holes and bring it smooth finish.
Approval For Execution
Contractor Site Engineer(Sign & Name) |  | Contractor QA/QC Engineer ( Sign & Name ) | PMC Engineer (Sign & Name) |  |  |  | Client Engineer ( Sign & Name )
D. Checks during Execution
16 | Dampen the surface before starting of coating application.
17 | Prepration of Brushbond mix is as per Manufacturer recommendations/ TDS.
18 | Application of First coat with recommended brush @ 1.5kg/sqm in 2 coats
19 | Lay Geofabric cloth after 1st coat and press firmly while the first coat is green
20 | Application of Second coat with recommended brush @ 1.5kg/sqm in 2coats with the interval of 4-6hrs depends upon climatic condition.
21 | Confirm that second coat is applied perpendicular to first coat after reaching dry state.
22 | Coating should be done on the entire horizonatl sutrface and should be extended vertically 600mm above SSL.
E. Protection Screed
23 | Ensure that there is no damage to water proofing coat prior to protection plaster
24 | Ensure the Protection plaster should be 12-15mm thickness Mix CM 1:4 with addition of Waterproofing compound(Conplast 421 IC) coating on wall as per methodology.
25 | Lay the protective screed concrete over second coat using 12 mm aggregates mix ratio of 1:2:4 Admixed with conplast 421 IC with a thickness of 60mm.
E. Post Execution Checks
26 | Post Ponding test should be done for 72 hrs as per approved methodology and if any leakges should be treated.. | [6 empty] | Start date: End date:
27 | Curing to be done atleast for 7 days
Remarks if Any
Final Approval
3 |  |  |  |  | Not approved (see Remarks)
Contractor Site Engineer(Sign & Name) |  | Contractor QA/QC Engineer ( Sign & Name ) | PMC Engineer (Sign & Name) |  |  |  | DTCPL(Client) ( Sign & Name )